## Task Breakdown
User Story Name | Task Name
Analysis | Review the task and prepare the task breakdown
Plan order of execution
Investigate what is unfamiliar
Check
Enter time for the analysis
Dynamics DEMO Tenant Setup | Setup the demo tenant
Setup accounts and licences
Setup azure account
Setup 2FA
Dev env setup | install required packages
setup kingswaytsoft account and licence
Data Model preparation | Setup the table
Add the fields
Setup view on app
SSIS integration | Create the SSIS project
Read the source spreadsheet
Map the columns to the Dataverse table
Load the data and verify the records
Azure Function API | Scaffold the isolated worker function
Connect to Dataverse with ServiceClient
Query active properties with paging
Map the entity to the response model
Handle errors and cancellation
Caching | Add HybridCache to the function
Wrap the repository with a cached decorator
Security and documentation | Add OpenAPI documentation for the endpoint
Add the access token middleware
Keep the access token in configuration
Verify the endpoint is protected
Performance testing | Make the cache TTL configurable
Add a cache on/off switch
Write the k6 load test
Run cached and uncached comparisons
Investigate the throughput difference

## Time Spent
User Story | Task | Started On | Time spent (round to 0,5h)
Analysis | Review the task and prepare the task breakdown | 2026-09-07 | 1
Analysis | Plan order of execution | 2026-09-07 | 0.5
Analysis | Investigate what is unfamiliar | 2026-09-07 | 0.5
Analysis | Check | 2026-09-07 | 0.5
Analysis | Enter time for the analysis | 2026-09-07 | 0.5
Dynamics DEMO Tenant Setup | Setup the demo tenant | 2026-09-07 | 1
Dynamics DEMO Tenant Setup | Setup accounts and licences | 2026-09-07 | 4.5
Dynamics DEMO Tenant Setup | Setup azure account | 2026-09-07 | 0.5
Dynamics DEMO Tenant Setup | Setup 2FA | 2026-09-07 | 0.5
Dev env setup | install required packages | 2026-09-07 | 1
Dev env setup | setup kingswaytsoft account and licence | 2026-09-07 | 0.5
Data Model preparation | Setup the table | 2026-09-07 | 0.5
Data Model preparation | Add the fields | 2026-09-07 | 0.5
Data Model preparation | Setup view on app | 2026-09-07 | 0.5
SSIS integration | Create the SSIS project | 2026-09-08 | 0.5
SSIS integration | Read the source spreadsheet | 2026-09-08 | 0.5
SSIS integration | Map the columns to the Dataverse table | 2026-09-08 | 0.5
SSIS integration | Load the data and verify the records | 2026-09-08 | 0.5
Azure Function API | Scaffold the isolated worker function | 2026-09-08 | 0.5
Azure Function API | Connect to Dataverse with ServiceClient | 2026-09-08 | 1
Azure Function API | Query active properties with paging | 2026-09-08 | 1
Azure Function API | Map the entity to the response model | 2026-09-08 | 0.5
Azure Function API | Handle errors and cancellation | 2026-09-08 | 0.5
Caching | Add HybridCache to the function | 2026-09-08 | 0.5
Caching | Wrap the repository with a cached decorator | 2026-09-08 | 1
Security and documentation | Add OpenAPI documentation for the endpoint | 2026-09-08 | 1.5
Security and documentation | Add the access token middleware | 2026-09-08 | 0.5
Security and documentation | Keep the access token in configuration | 2026-09-08 | 0.5
Security and documentation | Verify the endpoint is protected | 2026-09-09 | 0.5
Performance testing | Make the cache TTL configurable | 2026-09-09 | 0.5
Performance testing | Add a cache on/off switch | 2026-09-09 | 0.5
Performance testing | Write the k6 load test | 2026-09-09 | 1
Performance testing | Run cached and uncached comparisons | 2026-09-09 | 1
Performance testing | Investigate the throughput difference | 2026-09-09 | 1.5
|  | Total | 27